**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared:2025-03-08 |

Report Prepared By Team members:Darya Mansouri, Ali Roozbahani Mousavi, Ivan Zakrevskyi, Nut Jaroensri

Employer/Organization:

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | Cups & Cookies | |
| T-69 | |
| Start Date: **Feb 01, 2025** | End Date: **Mar 07, 2025** |
| Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary

|  |
| --- |
| **Project Status Summary** |
| The **Cups & Cookies** project is progressing well. The team has successfully implemented key features such as user authentication, recipe and product display, and user dashboards. The backend API for handling users, products, and orders is functional, and the frontend UI is nearing completion. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Implemented **user authentication** (registration, login, role-based access control) | Admin panel for viewing and managing products is not yet complete |
| Developed main page with links to products and recipes | Cart functionality needs further integration with database |
| Created recipes and product pages with category filtering | Payment method implementation is pending API integration |
| Designed and implemented dashboard for users with personal info update functionality | Some UI improvements are still required, including button alignments and styling fixes |
| Connected frontend to backend using API calls for product and recipe display |  |

Upcoming Objectives for **Mar 08, 2025 to Mar 27, 2025**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To  <name/s> | | Duration  <days> | Date |
| Implement Admin Product Management | Nut Jaroensri | | 5 days | March 5-March 10 |
| Complete Cart Functionality | Ali Roozbahani Mousavi | | 4 days | March 7-March 11 |
| Integrate Payment API | Ivan Zakrevskyi | | 6 days | March 10-March 16 |
| UI Fixes for Dashboard & Forms | Darya Mansouri | | 3 days | March 11- March 14 |
| Final Testing and Bug Fixes | Entire Team | | 5 days | March 18- March 23 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Product managment | | Nut Jeroensri | March 10 |
| Fully Functional Cart | | Ali Roozbahani Mousavi | March 11 |
| Payment Methos Integration | | Ivan Zakrevskyi | March 16 |
| UI & styling Updates Updates | | Darya Mansouri | March 14 |
| Complete system testing | | Entire Team | March 23 |

Managing Issues and Risk (for current reporting period and next period)

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| UI inconsistencies in forms and buttons | |  |  | | --- | --- | |  | Standardize CSS styles and ensure all elements are aligned | | March 14 |
| Payment API integration complexity | |  |  | | --- | --- | |  | Research and test multiple APIs to determine the best option | | March 16 |
| Cart database integration errors | Debug and fix API requests related to adding/removing items | March 11 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Delays in Admin Panel Development | |  |  | | --- | --- | |  | Med | | |  |  | | --- | --- | |  | Med | | Assign additional resources if necessary |
| Payment API incompatibility | High | High | Have a backup payment provider ready |
| |  | | --- | |  | | UI responsiveness issues | | Med | Low | |  |  | | --- | --- | |  | Implement thorough testing across devices | |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “W25\_T<team number>\_ProjectReport2”.

For e.g., W25\_T99\_ProjectReport2

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, Mar 09, 2025 (11:59 p.m.)**